FIELDOPS DASHBOARD 2.0

# Development Roadmap

Version 1.0
July 24, 2026
Derived from the Architecture Review and Architecture & Design Specification

Roadmap purpose This roadmap converts the approved architecture into a sequenced delivery plan. It defines release boundaries, task dependencies, exit criteria, validation requirements, and the order in which the codebase should be changed. The roadmap intentionally prioritizes trust and reliability before advanced features.

Status: APPROVED ARCHITECTURE BASELINE — ready for backlog creation and implementation planning

# 1. Approved Product Direction

| Decision | Approved direction | Roadmap consequence |
| --- | --- | --- |
| Architecture | Hybrid React UI + Local FieldOps Agent | The browser remains unprivileged; hardware and native actions move behind a trusted local service. |
| Agent model | Windows service + tray companion | The service owns telemetry and actions; the tray app owns health, settings, restart, logs, and diagnostics. |
| Database | SQLite | Configuration, logs, caches, acknowledgements, migrations, and audit data become durable local records. |
| User interface | Browser-based React | The UI stays portable and can evolve independently from the Windows integration layer. |
| Product behavior | Field Operations Assistant | Recommendations are part of the vision, but every recommendation must disclose source, assumptions, confidence, and limitations. |
| Scope | Disciplined field-radio operations | Features must directly support field setup, operating, safety awareness, logging, or application control. |
| Long-term vision | Trusted field assistant | The product should progress from dashboard to advisor without becoming autonomous or authoritative. |

Mission statement FieldOps Dashboard is a field-first operations platform for amateur-radio operators. It consolidates trusted telemetry, environmental awareness, operating guidance, logging, and application control into a single reliable interface that remains useful online and offline. Its goal is not merely to display information, but to help operators make better decisions while remaining transparent about the source and confidence of every value and recommendation.

# 2. Roadmap Principles

No advanced feature work begins until the dashboard stops presenting synthetic operational data as live.

Every release must leave the application in a deployable and testable state; unfinished architecture may be hidden behind feature flags.

Each subsystem is migrated end-to-end rather than partially refactored across several releases.

The local agent security boundary is designed before native application launching or software updating is enabled.

Every milestone includes tests, diagnostics, documentation, and field validation—not only code completion.

Existing visual design is preserved where it supports the field workflow, but misleading indicators are removed immediately.

Browser portability is retained by keeping hardware and Windows-specific logic outside React.

Recommendation features may use measured, cached, derived, or modeled inputs, but those states remain visible to the operator.

# 3. Release Map

| Release | Theme | Primary outcome | Architecture milestone |
| --- | --- | --- | --- |
| 2.2 | Trustworthy Dashboard | The existing application becomes honest about loading, source failure, stale data, and unsupported actions. | Shared telemetry contract introduced in the current architecture. |
| 2.3 | Local Agent Foundation | A secure Windows service, tray companion, SQLite store, and real local telemetry become operational. | Privileged browser/server responsibilities move into the agent. |
| 2.4 | Operational Integration | Real launcher execution, persistent logging, configuration migration, diagnostics, and reliable remote-data adapters. | Core field workflows use the agent and database end-to-end. |
| 2.5 | Field Operations Assistant | Corrected field tools, regional operating guidance, activation-plan recommendations, and dependable offline behavior. | The assistant layer is built on trusted data and explicit confidence. |
| 3.0 | Advanced Field Intelligence | True path prediction, mature planning, grounded AI, signed updating, and production release engineering. | Long-term architecture reaches full intended capability. |

# 4. Dependency Order

Telemetry contract and status presentation.

Agent security skeleton and health endpoint.

SQLite schema, migrations, and repository layer.

GPS and system telemetry adapters.

External-data scheduling and cache adapters.

Safe application registry and launcher.

Persistent logging and ADIF.

Corrected field tools and regional guidance.

Offline packaging, update system, and advanced assistant functions.

Critical path The launcher is not the first coding target even though it is highly visible. Safe launcher execution depends on the local agent, authentication, application registry, path policy, audit logging, and result contract. Beginning there would recreate the same architecture problem in a more dangerous form.

# 5. Version 2.2 — Trustworthy Dashboard

Objective: make the current application operationally honest before adding the local agent. This release removes the most dangerous prototype behavior and introduces the contracts that later releases will use.

## 5.1 Included work

| Task ID | Work item | Definition of done |
| --- | --- | --- |
| 2.2-01 | Shared telemetry envelope | Common status, source, observedAt, receivedAt, staleAfter, quality, error, and data types exist and are used by migrated panels. |
| 2.2-02 | Status UI components | Reusable LIVE, CACHED, STALE, MODELED, MANUAL, UNAVAILABLE, and ERROR indicators show source and age. |
| 2.2-03 | Remove fabricated defaults | Battery, GPS, network, CPU, memory, weather, solar, ionosonde, forecast, and log fixtures no longer appear as current data. |
| 2.2-04 | Weather and NOAA semantics | NOAA unavailable is distinct from zero alerts; weather and alert refreshes run independently. |
| 2.2-05 | Propagation honesty | Rename VOACAP to Regional HF Band Guidance; label derived/model outputs; remove synthetic station measurements. |
| 2.2-06 | GPS source guardrails | Remove Richmond active-fix fallback; add waiting, manual, last-known, stale, and unavailable states. |
| 2.2-07 | Disable misleading actions | Controls that do not work—launcher success animations, network switching, installation claims—are disabled or explicitly marked unavailable. |
| 2.2-08 | Correct zero/null behavior | Replace truthy fallbacks with null-safe logic where zero is valid. |
| 2.2-09 | Test foundation | Add unit and component-test framework, CI type checking, and core status-transition tests. |
| 2.2-10 | Centralized version metadata | Package, UI, user agent, ZIP, ADIF, and diagnostics use one version source. |

## 5.2 Exit criteria

Cold start displays no fabricated operational values.

Every migrated panel visibly communicates loading, live, cached, stale, unavailable, or error.

NOAA failure cannot be mistaken for no alerts.

No synthetic ionosonde station or weather forecast is presented as measured.

The launcher does not claim success when it cannot launch.

Automated tests cover telemetry status and key fallback transitions.

The current browser/Express application remains usable while the agent is still absent.

## 5.3 Field validation

Test connected, disconnected, and intermittent Internet conditions.

Test with browser geolocation allowed, denied, and unavailable.

Leave the dashboard stationary for several hours and verify weather/alert freshness behavior.

Confirm night-vision and sunlight modes make stale/error status distinguishable without relying only on color.

# 6. Version 2.3 — Local Agent Foundation

Objective: create the trusted Windows integration layer that will own hardware, privileged actions, persistence, and external-data normalization.

## 6.1 Included work

| Task ID | Work item | Definition of done |
| --- | --- | --- |
| 2.3-01 | Technology spike | Select service implementation language/runtime and browser-agent transport using a documented decision record and working prototype. |
| 2.3-02 | Windows service skeleton | Install, start, stop, restart, log, report version, and expose authenticated localhost health. |
| 2.3-03 | Tray companion | ADR-003 selects the tray technology and service-control authorization. Tray shows actual service state and authenticated health, requests a narrowly scoped restart, and reports genuine results. |
| 2.3-04 | Secure local API | Loopback binding, authentication, schema validation, size limits, rate limits, and restricted CORS. |
| 2.3-05 | SQLite foundation | Versioned schema, migrations, backup, recovery mode, repository abstraction, and audit tables. |
| 2.3-06 | Agent capability registry | UI can query supported hardware and operations rather than assuming they exist. |
| 2.3-07 | Serial-port enumeration | Return real ports, device names, availability, and configurable baud rates. |
| 2.3-08 | NMEA GNSS adapter | Checksum validation, core sentence parsing, fix freshness, disconnect/reconnect, and source priority. |
| 2.3-09 | Windows system telemetry | Real battery, CPU, memory, storage, and network information with nullable capability fields. Use Windows-provided battery runtime estimates, authoritative AC/battery source reporting, and supported-hardware runtime measurements. |
| 2.3-10 | Agent diagnostics | Structured logs, last error, adapter health, timestamps, and redacted diagnostic export. |

## 6.2 Architecture decision records required

ADR-001: Windows service runtime/language.

ADR-002: localhost HTTPS versus OS-authenticated IPC.

ADR-003: tray companion technology and service-control mechanism.

ADR-004: SQLite library, migration framework, and backup strategy.

ADR-005: browser launch and installation model for the local dashboard.

## 6.3 Exit criteria

The service installs and starts automatically on the ToughPad and ToughBook.

The browser can authenticate to localhost but an unrelated webpage cannot invoke privileged endpoints.

A user-selected COM port produces real GPS telemetry and recovers after unplug/replug.

Real system telemetry replaces all remaining static CPU, memory, battery, and network values.

SQLite migrations and rollback/recovery are tested.

The tray companion can identify and recover a stopped or unhealthy service.

# 7. Version 2.4 — Operational Integration

Objective: move the principal field workflows onto the local agent and durable database.

## 7.1 Included work

| Task ID | Work item | Definition of done |
| --- | --- | --- |
| 2.4-01 | Unified application registry | One typed catalog drives display, detection, launch, dependencies, URI schemes, and platform support. |
| 2.4-02 | Safe application launching | Approved app IDs launch through non-shell APIs with validated paths/arguments and explicit results. |
| 2.4-03 | Real application detection | Filesystem, registry, URI, package, and process checks report actual installation state. |
| 2.4-04 | Versioned configuration | Operator and machine profiles, schema migrations, validation, import preview, backup, and protected secrets. |
| 2.4-05 | Persistent SmartLog+ | SQLite QSO storage, empty initial log, activation sessions, edit/delete/undo, autosave, and crash recovery. |
| 2.4-06 | ADIF conformance | Validated import/export with UTC date/time, station callsign, mode, band/frequency, grids, and activation references. |
| 2.4-07 | Weather and alerts agent adapters | Scheduled retrieval, last-known-good cache, rate handling, service status, source timestamps, and source-specific polling intervals based on upstream cadence and field constraints. |
| 2.4-08 | Space-weather adapters | Real SWPC indices and ionosonde observations, including KC2G stations.json and authoritative measurement timestamps, with cache policy, source-specific polling, and measured/derived separation. |
| 2.4-09 | Audit and diagnostics | Launch, config, update, migration, and source-state events are inspectable and exportable in redacted form. |
| 2.4-10 | End-to-end field workflow tests | GPS acquisition, weather, alert outage, launch, QSO logging, restart, and offline recovery tested together. |

## 7.2 Exit criteria

Approved applications launch and report genuine success, failure, missing path, already running, or denied.

Imported configuration cannot directly create arbitrary command execution.

Logs persist across restart and exported ADIF passes the selected conformance test.

Weather and alerts remain understandable during partial source failures.

Configuration migrates safely between releases and supports backup/restore.

Diagnostic output is useful without leaking secrets or sensitive details by default.

# 8. Version 2.5 — Field Operations Assistant

Objective: begin delivering genuinely useful operating recommendations once their inputs are trustworthy.

## 8.1 Included work

| Task ID | Work item | Definition of done |
| --- | --- | --- |
| 2.5-01 | Correct SmartDeploy | Topology-specific dipole, EFHW, quarter-wave vertical, and random-wire guidance with validated assumptions. |
| 2.5-02 | Correct SmartFrequency | Complete versioned tables by band, regulatory region, license class, objective, and mode. |
| 2.5-03 | Regional guidance engine | NVIS, regional, continental, and DX guidance using measured/derived data, solar position, and explicit confidence. |
| 2.5-04 | Operating-plan recommendations | Recommend band/mode/order based on location, UTC, weather, space weather, available antennas, power, and operator objective. |
| 2.5-05 | Recommendation explanation | Every recommendation shows inputs, source status, reasoning summary, confidence, and limitations. |
| 2.5-06 | Offline-first application shell | Dashboard and local functions start without Internet; remote panels use last-known-good state correctly. |
| 2.5-07 | Operator equipment profile | Radios, antennas, amplifiers, batteries, deployment constraints, and preferred modes inform recommendations. |
| 2.5-08 | Activation workflow | Pre-operation checklist, active session context, quick logging, app launch, weather/alert awareness, and wrap-up export. |
| 2.5-09 | Field usability validation | Direct-sunlight, night, gloves/touch, weak network, low battery, and summit/campsite scenarios tested. |

## 8.2 Recommendation policy

The assistant advises; it does not automatically transmit, change radio settings, or launch a sequence without operator action.

Measured, cached, derived, and modeled inputs remain distinguishable in both recommendations and detail views.

Low-confidence or insufficient-data situations result in a qualified suggestion or no recommendation—not false precision.

Weather alerts and regulatory references outrank convenience recommendations.

## 8.3 Exit criteria

The assistant can produce a useful operating plan from a real field profile and current location.

Incorrect 80-meter fall-through frequency behavior is eliminated.

Antenna outputs are technically appropriate to the selected topology.

Offline startup supports GPS, telemetry, launcher, logging, and cached remote-data display.

Every recommendation is explainable and displays confidence/source limitations.

# 9. Version 3.0 — Advanced Field Intelligence

Objective: complete the long-term assistant vision without weakening the trust model established in 2.2-2.5.

## 9.1 Included work

| Task ID | Work item | Definition of done |
| --- | --- | --- |
| 3.0-01 | True path prediction | VOACAP or documented equivalent uses TX/RX locations, UTC/date, power, antennas, mode, and path objective. |
| 3.0-02 | Destination and activation planning | Evaluate future/manual locations without confusing planning coordinates with live GPS. |
| 3.0-03 | Grounded AI advisor | Optional assistant uses curated current references, citations where appropriate, rate limits, privacy controls, and advisory labeling. |
| 3.0-04 | Signed release pipeline | CI builds tagged artifacts, signs manifests/packages, publishes checksums, and records provenance. |
| 3.0-05 | Atomic updater and rollback | Stage, verify, migrate, health-check, switch, and automatically restore prior version on failure. |
| 3.0-06 | Encrypted profile transfer | Move operator profile and selected settings between ToughPad and ToughBook without exposing secrets. |
| 3.0-07 | Mature diagnostics | Health timeline, adapter history, launch/update audit, performance data, and support bundle. |
| 3.0-08 | Production hardening | Accessibility, threat review, dependency scanning, performance, recovery, and field beta closure. |

## 9.2 3.0 release gate

Path predictions identify model, inputs, time, and uncertainty.

AI output is optional, grounded, rate-controlled, and unable to invoke privileged actions.

Updates verify provenance and recover automatically from failure.

The application has completed a defined ToughPad/ToughBook beta cycle with no unresolved critical reliability defects.

Architecture documentation, API contracts, schema migrations, and recovery procedures match the shipped system.

# 10. Architecture Review Task Mapping

| Architecture task | Assigned release | Reason |
| --- | --- | --- |
| P0-01 Stop fabricated operational data | 2.2 | Immediate trust and safety defect. |
| P0-02 Define normalized source/freshness contract | 2.2 | Foundation for every later subsystem. |
| P0-03 Implement visible failure/stale states | 2.2 | Required before data adapters change. |
| P0-04 Separate NOAA unavailable from zero alerts | 2.2 | Safety-sensitive and independent of agent. |
| P0-05 Secure privileged API boundary | 2.3 | Agent foundation prerequisite. |
| P0-06 Design safe native launcher service | 2.3 design / 2.4 implementation | Security design precedes execution. |
| P0-07 Replace unsafe updater | 3.0 | Requires mature service, CI, signing, and rollback. |
| P1-01 Create Local FieldOps Agent | 2.3 | Core architecture milestone. |
| P1-02 Deterministic GPS source policy | 2.2 guardrails / 2.3 full implementation | Early honesty followed by hardware integration. |
| P1-03 Weather/alert scheduler and cache | 2.2 semantics / 2.4 agent implementation | Split to reduce risk. |
| P1-04 Replace propagation labels/synthetic model | 2.2 | Immediate trust repair. |
| P1-05 Persistent production logging | 2.4 | Depends on SQLite and agent. |
| P1-06 Version and validate configuration | 2.4 | Depends on schema and database. |
| P1-07 Automated test foundation | 2.2 onward | Begins immediately and expands each release. |
| P1-08 Correct SmartFrequency | 2.5 | Assistant/domain work after trusted foundation. |
| P1-09 Correct antenna calculator formulas | 2.5 | Assistant/domain work after trusted foundation. |
| P2-01 Genuine path prediction | 3.0 | Advanced model after regional guidance. |
| P2-02 Split monolithic React components | 2.2-2.5 incremental | Refactor alongside subsystem migrations. |
| P2-03 Offline-first shell | 2.5 | Depends on agent, cache, and durable local data. |
| P2-04 Harden AI advisor | 3.0 | Advanced optional feature. |
| P2-05 Unify app catalog and installer metadata | 2.4 | Required for safe launching. |
| P2-06 Observability and diagnostics | 2.3-3.0 incremental | Agent starts foundation; later releases deepen it. |
| P3-01 Accessibility and keyboard operation | 2.2 onward / 3.0 gate | Continuous requirement and final hardening. |
| P3-02 Centralize product versioning | 2.2 | Low effort, prevents release drift. |

# 11. Parallel Workstreams

| Workstream | Begins | Primary releases | Notes |
| --- | --- | --- | --- |
| Architecture and contracts | Immediately | 2.2-2.4 | Owns schemas, status semantics, API contracts, and ADRs. |
| React UI reliability | Immediately | 2.2-2.5 | Removes misleading states and consumes agent contracts. |
| Windows agent | After technology spike | 2.3-3.0 | Owns hardware, launch, storage, updates, and diagnostics. |
| Data adapters | 2.2 cleanup; 2.4 migration | 2.2-2.5 | Weather, alerts, SWPC, ionosonde, cache, schedules. |
| Logging and configuration | After SQLite foundation | 2.4 | Durable operator data and migration. |
| Assistant/domain logic | After trusted inputs | 2.5-3.0 | Antenna, frequency, guidance, operating plans, AI. |
| Quality and field testing | Immediately | All | Tests grow with every subsystem and release gate. |
| Release engineering | Basic in 2.2; full in 3.0 | 2.2-3.0 | Version metadata, CI, signed builds, update/rollback. |

# 12. Recommended First Implementation Sequence

The first coding cycle should be a narrow vertical slice that proves the architecture without attempting to build the entire agent.

| Order | Deliverable | Why first |
| --- | --- | --- |
| 1 | Create shared telemetry/status TypeScript types and status badge component. | Everything else depends on one definition of truth. |
| 2 | Convert weather/NOAA UI to loading/live/cached/stale/unavailable/error without synthetic fallback. | Weather is visible, safety-relevant, and exercises both data and UI contracts. |
| 3 | Add automated tests for weather and NOAA partial-failure scenarios. | Locks the desired behavior before backend changes. |
| 4 | Create minimal authenticated localhost agent health prototype. | Tests the chosen service/transport direction with little hardware complexity. |
| 5 | Build one end-to-end adapter through the agent—weather is the preferred candidate. | Proves browser-agent-external-source-cache flow. |
| 6 | Document lessons and confirm ADRs before broad migration. | Prevents scaling a flawed local-agent prototype. |

Do not start with Do not begin by implementing native launching, the updater, AI, true VOACAP, or a large React rewrite. Those tasks either require unfinished security foundations or create high churn before the core contracts are proven.

# 13. Initial Backlog Preparation Plan

## 13.1 Backlog artifacts to create before the first code change

One epic for Version 2.2 with tasks 2.2-01 through 2.2-10.

Acceptance-test cases copied from the 2.2 exit criteria.

ADR templates and the first five agent ADR placeholders.

A telemetry-envelope schema document and UI-state reference.

A source inventory identifying which current values are live, static, synthetic, or unsupported.

A feature-flag strategy for incomplete agent integrations.

A branch and pull-request policy for architecture work.

A release checklist and field-test log template.

## 13.2 Suggested first three iterations

| Iteration | Goal | Expected output |
| --- | --- | --- |
| Iteration 1 | Operational honesty foundation | Telemetry types, status components, default-data removal plan, test framework, version metadata. |
| Iteration 2 | Weather and NOAA vertical slice | Correct partial-failure states, refresh scheduling, cache semantics, automated tests. |
| Iteration 3 | Agent technology proof | Authenticated health endpoint, tray/service prototype decision, first ADRs, one adapter routed through agent. |

Iteration length is intentionally not prescribed. The work should be sized after backlog decomposition and repository-level implementation estimates rather than guessed from the architecture documents.

# 14. Roadmap Governance

Architecture-impacting changes require an ADR or specification amendment before implementation.

Every pull request identifies the roadmap task and release it serves.

No task is complete until its tests, operator-visible errors, diagnostics, and documentation are included.

New feature proposals must identify their field-operations purpose and must not bypass established source/security contracts.

Release scope changes are recorded explicitly; incomplete work is feature-flagged or deferred rather than shipped ambiguously.

Field-test findings can reprioritize reliability tasks ahead of roadmap dates.

## 14.1 Definition of done for roadmap tasks

| Area | Requirement |
| --- | --- |
| Function | Specified behavior works in normal and failure conditions. |
| Truthfulness | Source, age, state, and limitations are visible. |
| Security | Inputs and privileged boundaries follow the approved policy. |
| Persistence | Required data survives restart and migration. |
| Offline | Expected degraded behavior is implemented and tested. |
| Testing | Unit/integration/end-to-end coverage appropriate to the task exists. |
| Diagnostics | Failures are operator-visible and logged. |
| Documentation | Contracts, settings, and recovery steps are current. |
| Field validation | Applicable ToughPad/ToughBook scenario has been exercised. |

# 15. Major Delivery Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Agent technology choice made too quickly | Long-term packaging, service, and update problems. | Use a bounded prototype and ADR before committing. |
| UI and agent developed as separate big-bang projects | Contract drift and delayed integration. | Use vertical slices and shared typed contracts. |
| Launcher pressure bypasses security design | Local command-execution vulnerability. | Keep action disabled until registry/auth/audit are complete. |
| External APIs change or fail | Misleading or broken field data. | Adapter contracts, validation, cache, stale states, and recorded-response tests. |
| Scope expands into unrelated dashboard features | Reliability work stalls. | Apply mission statement and disciplined scope filter. |
| Assistant recommendations arrive before trusted inputs | Confident but wrong guidance. | 2.5 depends on completion of 2.2-2.4 release gates. |
| Updater is built before mature release pipeline | Bricked or compromised field installation. | Defer full updater to 3.0 and require signed artifacts/rollback. |
| Hardware differences between ToughPad and ToughBook | Adapter behavior diverges. | Capability discovery, nullable fields, mocks, and hardware acceptance tests. |

# 16. Roadmap Approval Position

The project is ready to move from architecture planning into backlog creation. It is not yet ready for undirected fixing. The first implementation work should be limited to the Version 2.2 trust foundation and a small local-agent proof of architecture.

Immediate next step Create the prioritized engineering backlog for Version 2.2, including task-level acceptance criteria, dependencies, likely files/components affected, test requirements, and recommended pull-request boundaries. Once that backlog is approved, implementation can begin with task 2.2-01.